## Linha Cronológica do Projeto
Project Plan
Start date:
2020-03-05
| May | [28 empty] | June | [29 empty] | July
| week nº 9 | [6 empty] | week nº 10 | [6 empty] | week nº 11 | [6 empty] | week nº 12 | [6 empty] | week nº 13 | [6 empty] | week nº 14 | [6 empty] | week nº 15 | [6 empty] | week nº 16 | [6 empty] | week nº 17 | [6 empty] | week nº 18 | [6 empty] | week nº 19 | [6 empty] | week nº 20 | [6 empty] | Duration
Phase: | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10 | 2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-17 | 2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24 | 2020-05-25 | 2020-05-26 | 2020-05-27
First Report | [84 empty] | 2 days
Poster and beta version | [84 empty] | 30 days
Final version | [84 empty] | 54 days
Api testing | [84 empty] | 14 days
Backoffice | [84 empty] | 14 days
Web application testing | [84 empty] | 7 days
Development of measures to protect user data (Let's Encript) | [84 empty] | 5 days
User restriction to some functionalities (black lists) | [84 empty] | 14 days
Save necessary data from deletes users (GDPR) | [84 empty] | 10 days
Protect our application from Cross site scripting and other possible attacks | [84 empty] | 7 days
Code review and possible reestructuring for better integration with clients | [84 empty] | 12 days
Development of the multi-login functionality (user can be logged in on multiple devices) | [84 empty] | 12 days
End-To-End tests e code inspection using SonarQube | [84 empty] | 9 days
Deploy Application | [84 empty] | End date
Formulas:
June = [week nº 13]+1