## Linha Cronológica do Projeto
Project Plan
Start date:
2020-05-31 | [56 empty] | COVID 19 PROJECT DELAY
|  | June | [29 empty] | Julho | [30 empty] | August | [30 empty] | September | [11 empty] | Duration
| week 13 | [6 empty] | week 14 | [6 empty] | week 15 | [6 empty] | week 16 | [6 empty] | week 17 | [6 empty] | week 18 | [6 empty] | week 19 | [6 empty] | week 20 | [6 empty] | week 21 | [6 empty] | week 22 | [6 empty] | week 23 | [6 empty] | week 24 | [6 empty] | week 25 | [6 empty] | week 26 | [6 empty] | week 27
Phase: | 2020-05-31 | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07 | 2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14 | 2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20 | 2020-06-21 | 2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27 | 2020-06-28 | 2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05 | 2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12 | 2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19 | 2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26 | 2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12
Poster and beta version | [105 empty] | 30 days
Final version | [105 empty] | 54 days
Api testing | [105 empty] | 14 days
Backoffice | [105 empty] | 12 days
Web application testing | [105 empty] | 7 days
Development of measures to protect user data (Let's Encript) | [105 empty] | 7 days
User restriction to some functionalities (black lists) | [105 empty] | 14 days
Save necessary data from deletes users (GDPR) | [105 empty] | 11 days
Protect our application from Cross site scripting and other possible attacks | [105 empty] | 7 days
Code review and possible reestructuring for better integration with clients | [105 empty] | Weekly
Development of the multi-login functionality (user can be logged in on multiple devices) | [105 empty] | 14 days
End-To-End tests e code inspection using SonarQube | [105 empty] | 11 days
Deploy Application | [105 empty] | 10 days
Formulas:
June = [week 13]+1
week 22 = [August]+1